## Sheet1
ID | Title | Status | Comment
4012 | Add date field in iKnow API | Failed | Not all items display the date field, only the last 2. See attachment. The search term doesnt matter. When I search for "news" or "test" iKnow results are different, ut only last 2 has date field.
4008 | Change: Profile - Modify notifications sections name for Communities | Failed | Renamed the wrong section. The one under "Engage email digest" should be renamed. That's the community notification section.
4018 | Defect: Communities suggested during the on-boarding process are 'lower-case' | Failed | community titles shouldn't have css "text-trasnform: capitalize;" on them.
4005 | Excessive spacing between last card and library | OK
INC2211441 - 4006 | My pages refiner resets the search string | Failed | still redirecting to an empty string search, or dos nothing when clicked on.
3428 | Phase 3 SIT My profile Followers displayed but not counted | OK
3979 | Related news query error | Skipped
3988 | HTTPS favorites page not working | Skipped | can't be tested, resources page doesn't work right now.
INC2203172 - 3483 | Phase 3 SIT Mobile Onboarding Next-Previous displayed in middle of screen | Skipped | can't be tested, don't have an iPhone.
INC2208912 - 4020 | Inside: Defect: Filter tags in Engage > All communities (Development) (INC2208912) | Failed | how should this work? I guess it should be displaying all the options in the filter dropdown? it seems like now it works this way: when no communities are filtered, all options are shown. when a filter is selected, the filtered communities' remaining options are shown. so if a community belongs to "English" but not to "Finance", then Finance will not be shown anymore.
INC2202884 - 3562 | Phase 3 SIT Mobile Search Communities spelling error | OK
INC2203464 - 3404 | Phase 3 SIT All communities Subject Filter contents not sorted alphabetically | OK
INC2202853 - 3786 | Phase 3 SIT My profile Content pagination displays only 10 items | OK
INC2202875 - 3585 | Phase 3 SIT Mobile Article location icon is blank | OK
INC2206582 - 4023 | Engage - Communities last activity not updated | Failed | Committed multiple posts, but last activity did not change.
INC2202834 - 3836 | My profile Activity stream PRIVATE MESSAGE displayed | OK
INC2203465 - 3353 | Phase 3 SIT “Guidelines & toolkits “ “Clear filters” shifted to second line | Skipped | cant be tested, resources page doesn't work right now.
INC2216164 - 3902 | My profile About me displays html formatting characters | OK
INC2208510 - 4027 | INSIDE News - image not appearing properly | OK
INC2202730 - 4013 | Community names in lower case only (INC2202730) | Failed | community titles shouldn't have css "text-trasnform: capitalize;" on them.
4022 | Wrong language in top navigation after changing preferred language | Failed | Part of the menu is changed partly not. See attachment.
INC2202868 - 3640 | INSIDE\Topics and Resources\Current\Deployment 1 (AM) - BugFixing | OK