## Sheet1
ID | Title | Status | Comment
3826 | News articles content images are not responsive (INC2202838) | OK
3839 | Regression Engage Follow more tags removes items with # character (INC2202832) | OK
4017 | Defect: Newly created Engage communities store the CommunityURL without the description data on the Communities List (INC2205640) | OK
3269 | Phase 3 SIT Sort order of Phase 3 tiles is not correct (INC2203495) | OK | Note: Can be sorted alphabetically, but still sorted by last modified date by default.
4006 | My pages refiner resets the search string (INC2211441) | OK
4030 | Spanish Translation - misspelling 'INISDE' (INC2221692) | OK
3967 | Access denied page on INSIDE always refers to Engage (INC2202768) | OK
3983 | Filter on news tagged for more than one department (INC2202626) | OK
4022 | Wrong language in top navigation after changing preferred language | FAILED | News and Resources are not translated to german when switched
4025 | Engage - Some menu items not changing to the user selected language (INC2213503) | FAILED | engage page still has "recommended colleagues" and "Recommended Communities" in sidebar
4ö35 | Inside misspell in Russian version (INC2211520) | OK
3988 | HTTPS favorites page not working | FAILED | Documents show an error, Applications are loaded OK.
3483 | Phase 3 SIT Mobile Onboarding Next-Previous displayed in middle of screen (INC2203172) | OK
4028 | Share doesn't work on INSIDE in Russian (INC2220093) | OK
3981 | Mouse hover on cards (INC2202628) | OK