## Sheet1
AM
ID | Title | Status | Comment
3938 | Community List webpart removed duplicates | Done
3623 | Phase 3 SIT Regression My profile About me now showing only one line | Done
3442 | Phase 3 SIT Edit community properties popup disappears from screen | Done
3816 | Top navigation no selected page indicator is displayed | Done
3448 | Phase 3 SIT My settings Notification text incorrect | Done
3585 | Phase 3 SIT Mobile Article location icon is blank | Committed | Location icon is not hidden when localisation is empty.
3463 | Phase 3 SIT My news left alignment not correct | Done
3836 | My profile Activity stream PRIVATE MESSAGE displayed | Committed | Not working for "My profile". "Privete message" still apper.
3818 | Regression Resources My Favorites does not use sentence case | Done
3787 | My profile Content tab doesn’t show all content types | Done
3834 | Regression News Articles are offset from MY NEWS title on all news pages | Done
3815 | Create Simple page Content area webpart edit arrow not displayed | Done
3347 | Phase 3 SIT Create page buttons should be in JTI Green colour | Done
3353 | Phase 3 SIT “Guidelines & toolkits “ “Clear filters” shifted to second line | Committed | "Clear filters" link is not displayed on left side of filters.
3980 | Engage – posting long strings of characters with no space causes overlap of text with right column menus | Done
3931 | No Clear filters button in Resources My favorites | Done
3786 | Phase 3 SIT My profile Content pagination displays only 10 items | Committed | No content is displayed on second page.
3579 | Phase 3 SIT Notifications First and last names should be in Bold | Done
3352 | Phase 3 SIT “My news” sort by is small and does not match other News pages | Done
3185 | Phase 3 SIT Page contents move when Refiners not displayed | Done
3508 | Phase 3 SIT My Settings page Footer bar is offset to the right by 10pixels | Done
3541 | Phase 3 SIT Unused Ideas options must be hidden | Done
3974 | All communities --> not all communities listed | Done
3282 | Phase 3 SIT My profile Tasks headings not aligned | Done
3547 | Phase 3 SIT Search Idea text is not corporate colour | Done
3404 | Phase 3 SIT All communities Subject Filter contents not sorted alphabetically | Committed | Still not sorted alphabetically
3542 | Phase 3 SIT Sentence case must be used with Campaign management screen | Done
3562 | Phase 3 SIT Mobile Search Communities spelling error | Committed | Still displays plural noun even when one follower is present
3564 | Phase 3 SIT Community Poll text extends out of input box | Done
3641 | Phase 3 SIT Mobile Search Responsive screen iKnow results overlapping other results | Done
3483 | Phase 3 SIT Mobile Onboarding Next-Previous displayed in middle of screen | Committed | Can't test on Iphone, please assign to someone who can.
3581 | Phase 3 SIT Mobile Hamburger Menu My pages scroll moves main page | Done
4001 | Wrong link in Application & Sites search results | Done
3985 | News on INSIDE not sorted by Article Date | Done
3977 | Typo on the Engage Create a Community form | Done
3835 | Regression Resources left navigation Trainings is incorrect English | Done
3640 | INSIDE\Topics and Resources\Current\Deployment 1 (AM) - BugFixing | Committed | People search not working yet on test site, it shows no results now.
3981 | Mouse hover on cards | Committed | Changeset 2473 -> text-decoration: none; atribute is in wrong css class
3965 | Library dropdown obscured by Ribbon | Done
3760 | Regression displayed Related Links are URLs not user friendly text | Done
Phase 3
ID | Title | Status
4002 | Modify the available videos after the onboarding | Done
3999 | Search results returning wrongly resource files | Done
3902 | My profile About me displays html formatting characters | Committed | I think this works as a description should work, but it does not fulfill the acceptance criteria. - Onboarding page Description field is empty [OK] - html formatting is either stripped entirely or cut from the first html character [not OK, should preserve html formatting] - Profile settings page doesn't allow to save when html characters are present. It allows saving multi-line text, but the profile page shows empty description. - Onboarding page doesnt allow to complete the last step if there are html characters in the description
3749 | Regression Onboarding Recommended communities corrupt | Done
4000 | Issue with accents | Done