## Overview
Status of the JTI TST test script:
Ref. | Cycle | Script | Passed | Failed | Blocked | No Run | Total | Executed | % exec | % OK
Sprint | - | JTI TST Script | 183 | 26 | 7 | 0 | 216 | 209 | 96.76% | 84.72%
Overview:
Ref. |  |  | Value
Release: |  |  | Sprint
Number of standard test cases planned: |  |  | 10
Number of release specific test cases planned: |  |  | 0
Start: |  |  | -
End: |  |  | -
Duration: |  |  | 2:30
Number of test resources: |  |  | 0
Number of issues resolved: |  |  | 0
Number of External systems issues discovered: |  |  | 0
Test environment used: |  |  | JTI TST

## Standard
Writer & date: | Durek Milan, 2017-09-23 |  |  |  |  | No Run
Passed
| JTI TST |  |  |  |  | Failed
Purpose: | 1 Test of index page | Failed
| 2. Test Engage page | Failed
| 3. Test News page | Passed
| 4. Test Resources page | Passed
| 5. Test Profile page | Failed
| 6. Edit my profile | Failed
| 7. Test Onboarding page | Failed
| 8. Test Resources /My Favorites and Recommended/ | Failed
| 9. Test Markets Topics | Passed
| 10. Log out | Passed
Prerequisite: | Your all browsing history is deleted (website files, cookies, history, Form data) |  | Start time | 9:41
Physical testcase: | 1 Test of index page |  | End time | 9:48
Overall status | Failed |  | Duration | 0:07
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Login on https://insedetest.jti.com | Own login details | User logged and the index page is loaded | Passed
2a | Check if are loaded all webparts |  | Global menu | Passed
2b |  |  | Corporate news | Passed
2c |  |  | My News | Passed
2d |  |  | Engage | Passed
3 | Click to cog button near My news title of webpart |  | Content of Manage my news is loaded in popup | Passed
4 | Click to text field "+add" and type any tag e.g. L&M -> Select tag from dropdown | L&M | Tag was found and added | Failed | L&M visible after 30 sec, after retyping
5 | In Markets tab tick checkboxes for Andorra, Canary Island and Spain to shown more that 10 articles and click Save |  | Selected Markets are added to tags (there is more that 10 articles together for this markets) | Passed
6 | Press F5 to reload site content |  | Site was reloaded | Passed
7 | Scroll down to count number of articles |  | There is 10 articles on site | Passed
8 | Wait a minute for loading infinite scroll |  | Next articles are loaded | Passed
9 | Check if webpart engage scroll down "Stick to top" automaticaly with scrolling |  | Engage webpart "Stick to top" when scrolling | Passed
10 | Scrolling back to top of site and check if the Engage webpart is on the original place |  | Engage webpart is on the original place | Passed
11 | Click to Seachbox in Top menu and type e.g."test" and press Enter | test | You are redirect to Resources -> All Content with correct results | Passed
12 | Click to Searchbox and write senseless text e.g. "asdf" | asdfg | No results found - Sorry, no results matching your search query | Passed
13 | 12:Click to Edit button on the right site of top menu |  | There is shown SP edit menu above top menu | Passed
14 | Click to Edit button again to hide SP edit menu |  | SP edit menu hide | Passed
15 | Click to Bell to shown notices |  | Notices are shown in dropdown menu | Passed
16 | Click again to Bell to hide notices |  | Notices are hide | Passed
Prerequisite: | User is logged |  | Start time | 9:49
Physical testcase: | 2. Test Engage page |  | End time | 10:34
Overall status | Failed |  | Duration | 0:45
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Click to Engage button from Top menu |  | Engage site loaded | Passed
2a | Check if are loaded all webparts |  | Top menu | Passed
2b |  |  | Left site navigation of communities | Passed
2c |  |  | Engage post my stream webpart | Passed
2d |  |  | Webpart Recognition | Passed
2e |  |  | Trending Tags | Passed
2f |  |  | Recommended colleagues | Failed | "RECOMMMENDED COLLEAGUES" instead of "RECOMMENDED"
2g |  |  | Recommended communities | Passed
4 | Click to Add post and add any comment and click Post | TestCom_[surname]_[iteration] | Post was added | Passed
5 | Click to Ask a question and add any question to any colleague and click Preview | TestCom_[surname]_[iteration] #Hastag_[surname]_[iteration] @[surname, name] | Question is OK | Passed
6 | Press on button Post |  | Question was added | Passed
7 | Click to created Hasttag page (#Hastag_[surname]_[iteration]) |  | Hastag page was opened in new tab | Failed | Hashtag tab not opened, but filtered posts
8 | Close the hashtag page tab (#Hastag_[surname]_[iteration]) |  |  | Blocked
9 | Click to All communities from left side navigation |  | All communities page is loaded on All communities tab | Passed
10 | Click to My communities tab |  | My communities are shown | Passed
11 | Check that there is 10 communities in the list, if yes, check pagination |  | There is 10 communities with pagination | Passed | works, but cannot scroll down fully to bottom causes flickering, prevents automation testing
12a | Click to Create a community button |  | Popup Create community is opened | Passed
12b |  | Name - Com_[surname]_[iteration] |  | Passed
12c |  | Access - Public |  | Passed
12d |  | Others details - Any texts/options |  | Passed
13 | Press on button Create community |  | *You have to wait to create community for a few minutes | Passed
14 | Click to All communities tab |  |  | Passed
15 | Choose 1 option from each of filters | Location - Andora; Department - Business Development; Brand - B and H; Language - English; Subject - Borough and district BA; Access - Public | Filter in dropdown menu is changed to chosen options and communities are filtered | Passed
16 | Click to Clear filter button for remove filter |  | Show all communities | Passed
17 | Check if there is 10 communities in list with check pagination |  | There is 10 communities with pagination | Passed
18 | Go to 2nd page of list of the all communities |  | Second page of list was loaded with correct pagination | Passed
19 | Click to “Join” to became a follower of public community |  | You are now follower of that community - button changed to Following | Passed
20 | Click to “Request to join” to request to join issent to the admin of private community |  | The request was sent to admin of that community | Failed | #2780 - works but not displayed in popup
21 | Hover on the “Following” button to show the button "leave" that community |  | The button "Leave" was shown | Passed
22 | Click to Searchbox in All Communities tab and type e.g. New created community "Name - Com_[surname]_[iteration]" and press enter | Name - Com_[surname]_[iteration] | Community with stated text are shown | Failed | #3390 - works but takes very long time to be searchable
23 | Open stated community e.g. New created community - Name - Com_[surname]_[iteration] (if you choose this community, you have to wait to done Time job in background to create this community*) /The community can be created up to 1 hour/ - If you do not want to wait, choose any public community | Name - Com_[surname]_[iteration] | Stated community is opened on Activity stream tab and in left side menu is the community marked by corporate colour | Passed | Opened fixed own community
24 | Public community - If you are following community click to Stop following community |  | The button changed to Follow community | Passed
25 | Public community - If you are not following community click to Follow community |  | The button changed to Stop following community | Passed
26 | Public community - click to invite others to follow |  | Open email client to send email with invitation | Passed
27 | Public community - click to Manage owners |  | Popup with owners is opened | Passed
28 | Close popup |  | Popup was closed | Passed
29 | Public community - click to Files tab |  | Files tab is shown with correct content with right site webpart | Passed
30 | Public community - click to Pictures tab |  | Pictures tab is shown with correct content with right site webpart | Passed
31 | Public community - click to Calendar tab |  | Calendar tab is shown with correct content with right site webpart | Passed
32 | Public community - click to Tasks tab |  | Tasks tab is shown with correct content with right site webpart | Passed
33 | Public community - click to Links tab |  | Links tab is shown with correct content with right site webpart | Passed
34 | Public community - click to Ideas tab |  | Ideas tab is shown with correct content with right site webpart | Passed | opened tab corretly, but scrolled down too much, top content not visible
35 | Public community - click to Admin settings tab |  | Admin settings tab is shown with correct content without right site webpart | Passed | opened tab corretly, but scrolled down too much, top content not visible
36 | Click to Edit Properties and check content |  | Popup is opened | Passed | Popup title bottom half is cut (y, g, q letters are not fully visible)
37 | Close popup |  | Popup was closed | Passed
38 | Click to Edit membership and check content |  | Site was opened in another window tab | Passed
39 | Close the last opened tab |  | Popup was closed | Passed
40 | Clict to Badges - edit community badges and check content |  | Popup was opened | Passed | Popup title bottom half is cut (y, g, q letters are not fully visible), double title
41 | Close popup |  | Popup was closed | Passed
42 | Click to Badges - setup automatic awarding of event based badges and check content |  | Popup was opened | Passed | Popup title bottom half is cut (y, g, q letters are not fully visible), double title
43 | Close popup |  | Popup was closed | Passed
44 | Click to Badges - manually award badges and check content |  | Popup was opened | Passed | Popup title bottom half is cut (y, g, q letters are not fully visible)
45 | Close popup |  | Popup was closed | Passed
46 | Click to Community engagement scorecard and check content |  | Opened in same frame | Passed
47 | Refresh page |  | Page was refreshed | Passed
48 | Click to Edit classifications and interests and check content |  | Popup was opened | Passed | Popup title bottom half is cut (y, g, q letters are not fully visible)
49 | Close popup |  | Popup was closed | Passed
50 | Click to Community visitors report and check content |  | Popup was opened | Failed | "Sorry, something went wrong"
51 | Close popup |  | Popup was closed | Passed
52 | Click to Email followers and check content |  | Popup was opened | Passed
53 | Close popup |  | Popup was closed | Passed
54 | Click to Recycle bin and check content |  | Recycled bin site is opened | Passed
Prerequisite: | User is logged |  | Start time | 10:46
Physical testcase: | 3. Test News page |  | End time | 10:54
Overall status | Passed |  | Duration | 0:08
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Click to News button from Top menu |  | My news site is opened | Passed
2 | Click to cog button near My news title |  | Popup is opened with content in tabs | Passed
3 | Scroll down to count number of articles |  | There is 10 articles on site | Passed
4 | Wait a minute for loading infinite scroll |  | Next articles are loaded | Passed
5 | Choose any tags from Filter by tags |  | Filter of articles by tags | Passed
6 | Choose 1 option from each of filters | Location - Andora; Department - IT; Brand - Silk Cut; Language - English; | Filter in dropdown menu is changed to chosen option, shown in filter and communities are filtered | Passed
7 | Click to Clear filter button for remove filters (dropdowns and tags) |  | Show all articles | Passed
8 | Click to All news from left side navigation |  | All news site is opened | Passed | No page title
9 | Choose any tags from Filter by tags |  | Filter of articles by tags | Passed
10 | Choose 1 option from each of filters | Whatever | Filter in dropdown menu is changed to chosen option, shown in filter and communities are filtered | Passed
11 | Click to Corporate news from left side navigation |  | Corporate news site is opened | Passed | No page title
12 | Choose any tags from Filter by tags |  | Filter of articles by tags | Passed
13 | Choose 1 option from each of filters | Whatever | Filter in dropdown menu is changed to chosen option, shown in filter and communities are filtered | Passed
14 | Click to Announcements from left side navigation |  | Annoucements site is opened | Passed | No page title
15 | Choose any tags from Filter by tags |  | Filter of articles by tags | Passed
16 | Choose 1 option from each of filters | Whatever | Filter in dropdown menu is changed to chosen option, shown in filter and communities are filtered | Passed
17 | Click to Jobs from left side menu |  | Content of site (blank tabs - Job search, Candidate, Job alert) | Passed
Prerequisite: | User is logged |  | Start time | 10:55
Physical testcase: | 4. Test Resources page |  | End time | 11:12
Overall status | Passed |  | Duration | 0:17
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Open link: https://insidetest.jti.com/EnterpriseSearchCenter/Pages/JTIresults.aspx?k=* |  | Resources site is opened in tab All content tab with 10 results in 1 page | Passed
2a | Check if there are loaded all webparts |  | Left side - Filter | Passed
2b |  |  | Right side - iKnow, People matches | Passed
3 | Choose any options from vertical left side filter to filter all content |  | All content are filtered | Passed
4 | Click to News tab button under Search box |  | News site is opened in Resources | Passed
5 | Check if there are loaded all webparts |  | Left side - Filter | Passed
6 | Choose any options from vertical left side filter to filter news |  | News are filtered | Passed
7 | Click to Resources tab button under Search box |  | Resources site is opened in Resources | Passed
8 | Check if there are loaded all webparts |  | Left side - Filter | Passed
9 | Choose any options from vertical left side filter to filter resources |  | Resources are filtered | Passed
10 | Click to People tab button under Search box |  | People site is opened in Resources | Passed
11 | Check if there are loaded all webparts |  | Left side - Filter | Passed
12 | Choose any options from vertical left side filter to filter people |  | People are filtered | Passed
13 | Click to Communities tab button under Search box |  | Communities site is opened in Resources | Passed
14a | Check if there are loaded all webparts |  | Left side - Filter | Passed
14b |  |  | Right side - Trending tags | Passed
15 | Choose any options from vertical left side filter to filter communities |  | Communities are filtered | Passed
Prerequisite: | User is logged |  | Start time | 11:14
Physical testcase: | 5. Test Profile page |  | End time | 11:30
Overall status | Failed |  | Duration | 0:16
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Click to Photo of user in right site of Global menu and choose My profile |  | My profile site is opened in Activity stream tab | Passed
2a | Check if there are loaded all webparts |  | Left side - Areas of expertise, My communities, Following, Followers | Passed
2b |  |  | Right side - Recommended communities, Recommended Colleagues | Passed
3 | Click to Add post and add any post and click Post | TestPost_[surname]_[iteration] | Post was added | Passed
4 | Click to Add a question and add any question and click Post | TestQuestion_[surname]_[iteration] | Question was added | Passed
5 | Click to Add private message and add any private message and click Send | TestPM_[surname]_[iteration] | Private message was post | Passed
6a | Find the last added post (point 3) |  |  | Passed
6b | * Click to "Like to" to like the post |  | The pos was liked | Passed
6c | * Click to "Comment to" to comment the post |  | The post was commented | Passed
6d | * Click to "Folllow-up" to follow-up the post |  | Now you are follow the post | Passed
6e | * Click to "Share to" to share the post |  | Pop-up is opened | Passed
7a | a) Choose Engage and type name of colleague (e.g. Karol Kocis) and click share. | Anybody from colleagues + Text of message | You shared this post with chosen colleague via Engage | Passed
7b | * Click to "Share to" to share the post |  | Pop-up is opened | Passed
8a | b) Choose Email and write email address of colleague and click share | Email address of your colleague + Text of message | Email client was opened | Passed
8b | * Click to button "more" and choose "Get link" |  | Link is shown in popup window | Passed
9 | Hover via post and on right side top of the post is shown dropdown arrow - click to it and choose Edit |  | Post is possible to edit | Passed
10 | Edit post and click save |  | Edited post is saved | Passed
11 | Hover via post and on right side top of the post is shown dropdown arrow - click to it and choose delete |  | The popup message with warning about remove post | Passed
12 | Click OK to remove the post |  | The post was removed | Passed
13 | Click to Organization tab |  | User is shown in hierarchy of company | Passed
14 | Click to Content tab |  | Tab is shown with correct content without side webparts | Passed
15 | Click to Tasks tab |  | Tab is shown with correct content without side webparts | Failed | Tab not displayed
16 | Click to Follow-up tab |  | Tab is shown with correct content without side webparts | Failed | Tab not displayed
17 | Click to Links tab |  | Tab is shown with correct content without side webparts | Failed | Tab not displayed
18 | Click to Add link in Links tab |  | Pop-up is opened | Blocked
19 | Fill out the form with correct data and click OK |  | The link is saved to chosen group and page is refreshing back to Links tab | Blocked
20 | Click to button "Manage links" |  | The site manage links was open in same tab | Blocked
21 | Check the box of the link and click edit links -> edit e.g. Field Title and click OK | Edit original title | The title was changed after automatically refres of site | Blocked
22 | Check the box of the link and click delete button |  | Warning message was shown | Blocked
23 | Click OK to remove the link |  | The link was removed | Blocked
Prerequisite: | User is logged |  | Start time | 11:30
Physical testcase: | 6. Edit my profile |  | End time | 11:55
Overall status | Failed |  | Duration | 0:25
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Click to Photo of user in right side of Top menu and choose Settings |  | Edit my profile site was opened | Passed
2 | Click to Profile in the left navigation |  | Profile webpart is shown in top of window and button Profile in the left navigation is highlighted | Passed
3 | Click to "Your preferred language" dropdown in Profile webpart and change language to e.g.Deutsch | Deutsch | The site is automatically reload and the language is changed to German | Failed | Did not reload automatically, language not changed
4 | Click to "Your preferred language" dropdown in Profile webpart and change language back to English | English | The site is automatically reload and the language is changed back to English | Failed | Did not reload automatically, language not changed
5 | Go to "About me" field and insert text | Insert this test to profile...Insert this test to profile...Insert this test to profile...Insert this test to profile..Insert this test to profile...Insert this test to profile..Insert this test to profile...Insert this test to profile...OKERROR | Text is finished with word OK (word ERROR was removed) = max characters 240 | Passed
6 | Change any others details in profile |  |  | Passed | Saved changes, but gave error "User profile update failed"
7 | Click to Expertise in the left navigation |  | Manage my expertise tags webpart is shown in top of window and button Expertise in the left navigation is highlighted | Failed | Menu item not highlighted, only after page reload
8 | Click to add topics and type text of item to field e.g. Camel and select one of suggestions | #CAnC_Academy | System will show auto-complete suggestions of existing terms and will be added among the tags | Failed | Can add tags, but no suggestions
9 | Click to News in the left navigation |  | Manage my news tags webpart is shown in top of window and button News in the left navigation is highlighted | Failed | Menu item not highlighted, only after page reload
10 | Click to text field "+add" and type any tag e.g. L&M -> Select tag from dropdown | L&M | Tag was found and added | Failed | Autocomplete takes long time to show (30 seconds)
11 | In tab Markets, Departments and Brands select any items |  | Ticked items was added among tags according the rules (1st Markets, 2nd Departments, 3rd Brands) | Passed
12 | Click to Notifications in the left navigation |  | Notifications webpart is shown in top of window and button Notifications in the left navigation is highlighted | Failed | Menu item not highlighted, only after page reload
13 | Change any details e.g. Communities |  | There are new selected communities | Passed | Saved changes, but gave error "User profile update failed"
14 | Click to Colleagues in the left navigation |  | Colleagues webpart is shown in top of window and button Colleagues in the left navigation is highlighted | Failed | Menu item not highlighted, only after page reload
15 | Click to Add colleagues in Colleagues webpart |  | Popup was opened | Passed
16 | Click to button "Browse" under 1st textbox to open Colleague find popup |  | Colleagued find popup was opened | Passed
17 | To field "Find" type name of any colleague e.g. "Peter Aker" and press Enter | Peter Aker | Peter Aker was found | Passed
18 | Click to Found employee in results and after that click to Add and confirm with button OK |  | Peter Aker was added to Colleague Textbox | Passed
19 | In popup Add colleagues press OK |  | Edit my pages site is reload and open reloaded page in #Notification webpart and selected colleague was added among the colleague in this webpart | Failed | Colleague was not Added, Page didn’t opened at #Colleagues Webpart
20 | Tick the checkbox near of any colleague e.g. "Peter Aker" and click to Remove colleagues |  | Warning window was open | Passed
21 | Click to OK to remove the colleague from the list |  | Edit my pages site is reload and open reloaded page in #Colleagues webpart and selected colleague was removed from the list | Failed | Colleague was deleted OK, but didn't open page at #Colleagues after reload
22 | Click to button "Save changes" to save the changes and check it |  | Notification was shown on bottom of page (User Profile updated) | Failed | Saved changes, but gave error "User profile update failed"
23 | Refresh the page and check the saved changes |  | The changes was saved | Passed | Saved changes, but gave error "User profile update failed"
Prerequisite: | User is logged |  | Start time | 11:55
Physical testcase: | 7. Test Onboarding page |  | End time | 12:05
Overall status | Failed |  | Duration | 0:10
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Open link https://insidetest.jti.com/Pages/Onboarding.aspx |  | Onboarding site is opened with menu | Passed
2 | Click to "Your preferred language" dropdown in "Introduction to Inside" webpart and change language to e.g.French | Francais | The site is automatically reload and the language is changed to French | Passed
3 | Click to "Your preferred language" dropdown in "Introduction to Inside" webpart and change language back to English | English | The site is automatically reload and the language is changed back to English | Passed
4 | Try to click to top menu to move between the steps |  | Moving among the steps is not possible | Passed
5 | On 1st Instroduction to Inside tab change the options and click next button |  | Next page Manage my news tags was opened | Passed
6 | Check if the content is loaded correctly |  | The content is loaded succesfully | Passed
7 | On 2nd Manage my news tags tab click next button |  | Next page Connect with colleagues was opened | Passed
8 | Check if the content is loaded correctly |  | The content is loaded succesfully | Failed | No mathing colleagues
9 | On 3rd Connect wiht colleagues tab click next button |  | Next page Join communities was opened | Passed
10 | Check if the content is loaded correctly |  | The content is loaded succesfully | Passed
11 | On 4th Join communities tab click next button |  | Next page Personalize profile was opened | Passed
12 | Check if the content is loaded correctly |  | There are webparts Personalize my profile content and Manage my expertise tags | Passed
13 | On 5th Personalize profile tab click next button |  | Next page Define notification was opened | Passed
14 | Check if the content is loaded correctly |  | The content is loaded succesfully | Passed
15 | On 6th Define notifications tab click to button Complete to finish |  | You are redirected to Index page | Passed | Takes long time to process (20 sec)
Prerequisite: | User is logged |  | Start time | 12:06
Physical testcase: | 8. Test Resources /My Favorites and Recommended/ |  | End time | 12:25
Overall status | Failed |  | Duration | 0:19
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Click to My Pages from top menu | Or click to Resources from Top menu navigation | Dropdown menu is shown | Passed
2 | Click to "See all" from dropdown menu |  | The site My favorites is opened and in left side navigation My favorites is marked | Passed
3a | Check if all webparts are loaded |  | Left hand menu with: | Passed
|  |  | My favorites | Passed
|  |  | Recommended | Passed
|  |  | Applications & sites | Passed
|  |  | Guidelines & toolkits | Passed
|  |  | Policies & procedures | Passed
|  |  | Reports & case studies | Passed
|  |  | Templates | Passed
|  |  | Training | Passed
3b |  |  | My applications & sites | Passed
3c |  |  | My saved documents | Passed
3d |  |  | My pages only with "-" icon | Passed
4 | Click to Recommended in left side navigation |  | Site Recommended si loaded and in left side naviagation Recommended is marked | Passed
5a | Check if all webparts are loaded |  | My applications & sites with pagination | Failed | Loaded webpart, but No results
5b |  |  | My saved documents with pagination | Failed | Loaded webpart, but No results
5c |  |  | Recommended My pages | Failed | Loaded webpart, but No results
6 | Try to filter documents |  | Documents are filtered | Failed | No results to filter
7 | Click on Applications & sites in left hand menu |  | There is shown 8 app and sites with paginations | Passed
8 | Click on Guidelines & toolkits in left hand menu |  | There is shown 8 docs with paginations | Passed
9 | Click on Policies & procedures in left hand menu |  | There is shown 8 docs with paginations | Passed
10 | Click on Reports & case studies in left hand menu |  | There is shown 8 docs with paginations | Passed
11 | Click on Templates in left hand menu |  | There is shown 8 docs with paginations | Passed
12 | Click on Training in left hand menu |  | There is shown 8 docs with paginations | Passed
13 | Go to right side webpart Recommended and click on external link |  | New tab window is opened | Failed | No links displayed
Prerequisite: | User is logged |  | Start time | 12:26
Physical testcase: | 9. Test Markets Topics |  | End time | 12:28
Overall status | Passed |  | Duration | 0:02
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Open link https://insidetest.jti.com/Markets/HQ/Pages/Topics_Landing.aspx to load "Topics_landing_page" |  | The site Topics Landing is loaded | Passed
2 | Open link https://insidetest.jti.com/Markets/HQ/Pages/Topics_Brand.aspx to load "Topics_brand_page" |  | The site Topics Brand is loaded | Passed
3 | Open link https://insidetest.jti.com/Markets/HQ/Pages/Topics_Generic.aspx to load "Topics_generic_page" |  | The site Topics Generic is loaded | Passed
4 | Open link https://insidetest.jti.com/Markets/HQ/Pages/Topics_Simple.aspx to load "Topics_simple_page" |  | The site Topics Simple is loaded | Passed
Prerequisite: | User is logged |  | Start time | 12:28
Physical testcase: | 10. Log out |  | End time | 12:29
Overall status | Passed |  | Duration | 0:01
| Action / Description | Value/User Test Data | Expected Result | Pass/Fail | Defect
1 | Click to Photo of user in right site of Top menu and choose Log out |  | Log out pop-up was opened | Passed
2 | Click to Log out to log out and exit window |  | You are logged out and the notification about closing window is shown | Passed
3 | Press Yes to close window |  | Internet browser was closed | Passed

## Test Automation Calculations
Test Automation Calculations
Number of Test cases | 10 | Number of browsers | 1
Number of test steps | 216 | Languages | 1
Number of Tast cases in Test Automation point of view | 22 | UI change possibility | 1
FTE | 0.5 | No Independent test environment | 1
Estimated time for preparation of the automated test cases (Hours) | 192 | Common Risk | 2
Estimated time for preparation of the automated test cases (Working Days) | 24 | Risk Factor | 0.5
Note on D6: Hudak, Szabolcs: In Test Automation point of view one test case contains about 1o test steps. This is one unit with we can count
Note on F6: Hudak, Szabolcs: This value can be 0 or 1
Note on F7: Hudak, Szabolcs: This value can be 0 or 1
Note on D8: Hudak, Szabolcs: Based on test automation experiences one engineer can automate approximately 3 test cases per day in the ideal word. Right now we count with half FTE and count with additional tasks and risks based on the checklist